## Sprint-5
| Requirement Status | [11 empty] | Dev Status
Sprint | Req. Confr | JIRA | Story Card | Subtasks/Tasks | Task Level Points | Story Points | Developer | Target Week | Revised Target Week | Requirement Status | Precon walkthrough Y/N | If "Y" Walkthrough Date? | Developer | Hrs | Dev Status | Dev Target completion date | Actual completion date | Remarks
5 | CONFR-2835 | 3508 | Requirements: Connect_Submission_Watercrafts details and navigation/territories (excl accessories) and Add'l Insured Fields_PC_F&R | Submission_Watercrafts details and navigation/territories (excl accessories) and Add'l Insured Fields_PC_F&R |  | 10 |  |  |  | Draft | N |  | Gulshan / Sathish | 64 | Yet to start
5 | CONFR-2837 | 3035 | Requirements: Connect_Submission_Watercrafts details and navigation/territories (excl accessories) and Add'l Insured - BR's and UW Issues_PC_F&R | Submission_Watercrafts details and navigation/territories (excl accessories) and Add'l Insured - BR's and UW Issues_PC_F&R |  | 4 |  |  |  |  | N |  | Gulshan / Sathish | 64
5 | CONFR-2871 | 3012 | Requirements: Connect_PC Account_Account Submission Manager_PC_All | PC Account_Account Submission Manager_PC_All |  | 2 |  |  |  | Draft | Y | 2018-09-27 | Swathi | 8 |  |  |  | All OOTB no change
5 | CONFR-2873 | 3010 | Requirements: Connect_PC Account_Account Documents_PC_All | PC Account_Account Documents_PC_All |  | 4 |  |  |  | Draft | Y | 2018-09-27 | pavani | 16 |  |  |  | Dev completed.
5 | CONFR-2874 | 3009 | Requirements: Connect_PC Account_Account UW Files_PC_All | PC Account_Account UW Files_PC_All |  | 4 |  |  |  | Draft | N |  | sreenivasareddy | 16 |  |  |  | on change on UW issue Screen
5 | CONFR-2875 | 3008 | Requirements: Connect_PC Account_Related Accounts_PC_All | PC Account_Related Accounts_PC_All |  | 4 |  |  |  | Draft | Y | 2018-09-27 | Sivakumar | 16 |  |  |  | One typelist value needs to be added
5 | CONFR-2843 | 3029 | Requirements: Connect_Submission_Recreational Vehicles (Screen fields and Validations)_PC_F&R | Submission_Recreational Vehicles (Screen fields and Validations)_PC_F&R |  | 10 |  |  |  | Draft | N |  | sruthi | 40
5 | CONFR-2845 | 3027 | Requirements: Connect_Submission_Recreational Vehicles (BR's and UW Issues)_PC_F&R | Submission_Recreational Vehicles (BR's and UW Issues)_PC_F&R |  | 5 |  |  |  | Draft | N |  | Sumalin | 16 |  |  |  | One UW issue
5 | CONFR-2853 |  | Requirements: Connect_Submission_UAV's/UAS (Screen and Validations)_PC_F&R |  |  | 8 |  |  |  |  | N | [6 empty] | Similar to 2843
5 | CONFR-2819 | 3051 | Requirements: Connect_Submission_Watercraft Details Fields_PC_F&R | Submission_Watercraft Details Fields_PC_F&R |  | 8 |  |  |  | No Document | N
5 | CONFR-2821 | 3049 | Requirements: Connect_Submission_Watercraft Details BR & UW Issues_PC_F&R | Submission_Watercraft Details BR & UW Issues_PC_F&R |  | 4 |  |  |  | No Document | N
5 | CONFR-2823 | 3047 | Requirements: Connect_Submission_UAV Details Fields_PC_F&R | Submission_UAV Details Fields_PC_F&R |  | 8 |  |  |  | No Document | N
5 | CONFR-2825 | 3045 | Requirements: Connect_Submission_UAV Details BR & UW Issues_PC_F&R | Submission_UAV Details BR & UW Issues_PC_F&R |  | 4 |  |  |  | No Document | N
5 | CONFR-2828 | 3042 | Requirements: Connect_Submission_Watercraft Operator Fields_PC_F&R | Submission_Watercraft Operator Fields_PC_F&R |  | 7 |  |  |  | No Document | N
5 | CONFR-2829 | 3041 | Requirements: Connect_Submission_Watercraft Operator BR & UW Issues_PC_F&R | Submission_Watercraft Operator BR & UW Issues_PC_F&R |  | 5 |  |  |  | No Document | N
5 | CONFR-2832 | 3038 | Requirements: Connect_Submission_Watercraft Operator Accident Details Fields_PC_F&R | Submission_Watercraft Operator Accident Details Fields_PC_F&R |  | 7 |  |  |  | No Document | N
5 | CONFR-2833 | 3037 | Requirements: Connect_Submission_Watercraft Operator Accident Details BR & UW Issues_PC_F&R | Submission_Watercraft Operator Accident Details BR & UW Issues_PC_F&R |  | 5 |  |  |  | No Document | N
5 | CONFR-2839 | 3033 | Requirements: Connect_Submission_Watercrafts accessory details (screen elements and field validations)_PC_F&R | Submission_Watercrafts accessory details (screen elements and field validations)_PC_F&R |  | 7 |  |  |  | Rejected as mentioned in comments | N
5 | CONFR-2841 | 3031 | Requirements: Connect_Submission_Watercrafts accessory details BR's and UW Issues_PC_F&R | Connect_Submission_Watercrafts accessory details BR's and UW Issues_PC_F&R |  | NA |  |  |  | Rejected as mentioned in comments | N
5 | CONFR-2855 | 3023 | Requirements: Connect_Submission_UAV's/UAS (BR's and UW Issues)_PC_F&R | Submission_UAV's/UAS (BR's and UW Issues)_PC_F&R |  | 5 |  |  |  |  | N | [6 empty] | Similar to 2843
5 | CONFR-2856 | 3022 | Requirements: Connect_Submission_Basic Vehicle Information Framework and Functionality_PC_Auto | Submission_Basic Vehicle Information Framework and Functionality_PC_Auto |  | 5 |  |  |  | Draft | N |  | Ravi | 24 |  |  |  | change to 4 fields
5 | CONFR-2858 | 3020 | Requirements: Connect_Submission_Line Coverages (Screen and Validations)_PC_F&R | Submission_Line Coverages (Screen and Validations)_PC_F&R |  | 4 |  |  |  | No dev required & No document available | N |  |  | 8
5 | CONFR-2865 | 3018 | Requirements: Connect_Submission_Line Coverages (BR's and UW Issues)_PC_F&R | Submission_Line Coverages (BR's and UW Issues)_PC_F&R |  | 4 |  |  |  | No dev required & No document available | N |  |  | 8
5 | CONFR-2867 | 3016 | Requirements: Connect_Submission_State Level Coverages (Screen and Validations)_PC_F&R | Submission_State Level Coverages (Screen and Validations)_PC_F&R |  | 4 |  |  |  | No dev required & No document available | N |  |  | 8
5 | CONFR-2869 |  | Requirements: Connect_Submission_State Level Coverages (BR's and UW Issues)_PC_F&R |  |  | 4 |  |  |  | No dev required | N |  |  | 8
|  | 3254 |  | Admin Data Loader | [6 empty] | Y |  | Siva |  | Pending |  |  | Need some more clarification
| CONFR-568 | 3255 | Requirements: Connect_Location_Structures_PC_FR | Locations_Structures_UW Issues | [6 empty] | Y |  | Shereen |  | Pending |  |  | Need to do Code review
| Confr-566 | 3256 | Requirements: Connect_Location_Dwellings_PC_FR | Locations_Dwellings_UW Issues | [6 empty] | Y |  | Gulshan |  | Pending |  |  | Need to do Code review
| CONFR-568 | 2419 | Requirements: Connect_Location_Structures_PC_FR | Location_Structures_Business Rules | [6 empty] | Y |  | Shereen |  | Blocker |  |  | No BR for Strutures
| Confr-566 | 2418 | Requirements: Connect_Location_Dwellings_PC_FR | Location_Dwellings_Business Rules | [6 empty] | Y |  | Sathish |  | Blocker |  |  | Pending with BA(Windhail dependency)
| Confr-570 | 1057 | Requirements: Connect_Location_Kentucky Tax_PC_FR | Location_Kentucky Tax_PC_FR | [6 empty] | Y |  | Sathish |  | Pending |  |  | Need to do Code review
|  | 3142 | Requirements: Connect_Driver_Driver Assignments_PC_FA (Field Specs and Validations) | [7 empty] | Y |  | Onsite dev
|  | 3143 | Requirements: Connect_Driver_Driver Assignments_PC_FA (BR's and UW Issues) | [7 empty] | Y |  | Onsite dev
|  | 3144 | Requirements: Connect_Driver_Driver Details_PC_FA (BR's and UW Issues) | [7 empty] | Y |  | Onsite dev

## Look Up
Requirement Status | Dev Status
No dev required & No document available | Yet to start
Requirement not available | WIP
Draft | Pending
Rejected | Blocker
Not in Scope | Completed
Deployed