## Sheet1
ssue Type | Issue key | Issue id | Summary | Week | Target Deployment date | Remarks
Story | CONFR-3258 | 342292 | GW_9.0.5 Accelerator Installation for Rating ( UI Field Mapping) | Week1 |  | Onsite is working on this. Per JIRA, code is deployed yesterday.
Story | CONFR-3256 | 342139 | Locations_Dwellings_UW Issues | Week2 |  | Update due date.
Story | CONFR-3255 | 342138 | Locations_Structures_UW Issues | Week2 |  | Move the dev card and sub task status. Update due date.
Story | CONFR-3254 | 342135 | Admin Data Loader (Dev) | Week3 |  | Get a clarity on who is working.
Story | CONFR-3218 | 341914 | Driver_Driver Details_PC_FA (BR's and UW Issues) | Week2 |  | Onsite
Story | CONFR-3217 | 341913 | Driver_Driver Assignments_PC_FA (Field Specs and Validations) | Week2 |  | Onsite
Story | CONFR-3215 | 341911 | Driver_Driver Assignments_PC_FA (BR's and UW Issues) | Week2 |  | Onsite
Story | CONFR-3148 | 341470 | Updated Roles Tab For Officers/Trustee/Partner/Members | Week1 |  | Onsite
Story | CONFR-3020 | 339130 | Submission_Line Coverages (Screen and Validations)_PC_F&R | Week3 |  | Per JIRA, no configuration effort involved.
Story | CONFR-3018 | 339126 | Submission_Line Coverages (BR's and UW Issues)_PC_F&R | Week3 |  | Per JIRA, no configuration effort involved.
Story | CONFR-3016 | 339124 | Submission_State Level Coverages (Screen and Validations)_PC_F&R | Week3 |  | Per JIRA, no configuration effort involved.
Story | CONFR-3014 | 339121 | Submission_State Level Coverages (BR's and UW Issues)_PC_F&R | Week3 |  | Per JIRA, no configuration effort involved.
Story | CONFR-2419 | 335305 | Location_Structures_Business Rules | Week2 |  | As per Ganesh's email, the BR is moved out of F&R. Need confirmation if we can defer this card.
Story | CONFR-2418 | 335304 | Location_Dwellings_Business Rules | Week2 |  | As per Ganesh's email, few BRs were moved of scope of Dwelling due to dependency on 'Wind hail lookup tab' and some UW issues to be handled as part of a future card. He has logged clarification in JIRA for the same. Dev-Card is blocked in JIRA because of this.
Story | CONFR-1057 | 327514 | Location_Kentucky Tax_PC_FR | Week1 |  | Change the dev card and sub task's status. Update due date.
Story | CONFR-3213 | 341858 | Product Model Viewer_9.0.5_ Installation | Week1 |  | Onsite
Story | CONFR-3051 | 339167 | Submission_Watercraft Details Fields_PC_F&R | Week3 |  | Sub-task is created. Please update due date after today's pre-con.
Story | CONFR-3029 | 339141 | Submission_Farm Vehicles (Screen fields and Validations)_PC_F&R | Week3 | 2018-10-12 | Sub-task status should be changed and comments should be added.
Story | CONFR-3027 | 339139 | Submission_Farm Vehicles (BR's and UW Issues)_PC_F&R | Week3 | 2018-10-12 | Sub-task status should be changed and comments should be added.
Story | CONFR-3012 | 339117 | PC Account_Account Submission Manager_PC_All | Week1 | 2018-10-05 | Ready for testing.
Story | CONFR-3010 | 339115 | PC Account_Account Documents_PC_All | Week1 | 2018-10-08 | Update sub-task status and comments.
Story | CONFR-3009 | 339114 | PC Account_Account UW Files_PC_All | Week1 | 2018-10-08 | Update sub-task status and comments.
Story | CONFR-3008 | 339113 | PC Account_Related Accounts_PC_All | Week1 | 2018-10-08 | Update sub-task status and comments.
Story | CONFR-2160 | 333632 | Driver_Driver Details_PC_FA (Field Specs and Validations) | Week2 |  | Onsite is working on this. Per JIRA, comments there is requirement clarification needed.
Story | CONFR-3508 |  | Submission_Watercrafts details and navigation/territories (excl accessories) and Add'l Insured Fields_PC_F&R |  | 2018-10-16 | Update sub-task status and comments.
Story | CONFR-3035 |  | Submission_Watercrafts details and navigation/territories (excl accessories) and Add'l Insured - BR's and UW Issues_PC_F&R |  | 2018-10-16 | Update sub-task status and comments.
Story | CONFR-3049 |  | Submission_Watercraft Details BR & UW Issues_PC_F&R |  |  | Sub-task is created. Please update due date after today's pre-con.
Story | CONFR-3047 |  | Submission_UAV Details Fields_PC_F&R |  |  | Cancelled card.
Story | CONFR-3045 |  | Submission_UAV Details BR & UW Issues_PC_F&R |  |  | Cancelled card.
Story | CONFR-3042 |  | Submission_Watercraft Operator Fields_PC_F&R |  | 2018-10-16 | Change the dev card and sub task's status. Update comments.
Story | CONFR-3041 |  | Submission_Watercraft Operator BR & UW Issues_PC_F&R |  | 2018-10-16 | Change the dev card and sub task's status. Update comments.
Story | CONFR-3038 |  | Submission_Watercraft Operator Accident Details Fields_PC_F&R |  |  | Cancelled card.
Story | CONFR-3037 |  | Submission_Watercraft Operator Accident Details BR & UW Issues_PC_F&R |  |  | Cancelled card.
Story | CONFR-3033 |  | Submission_Watercrafts accessory details (screen elements and field validations)_PC_F&R |  |  | Cancelled card.
Story | CONFR-3031 |  | Connect_Submission_Watercrafts accessory details BR's and UW Issues_PC_F&R |  |  | Cancelled card.
Story | CONFR-3023 |  | Submission_UAV's/UAS (BR's and UW Issues)_PC_F&R |  |  | Cancelled card.
Story | CONFR-3022 |  | Submission_Basic Vehicle Information Framework and Functionality_PC_Auto |  |  | Sub-task is created. Please update due date after today's pre-con.
Story | CONFR-3142 |  | Requirements: Connect_Driver_Driver Assignments_PC_FA (Field Specs and Validations) |  |  | Handled in CONFR-3217
Story | CONFR-3143 |  | Requirements: Connect_Driver_Driver Assignments_PC_FA (BR's and UW Issues) |  |  | Handled in CONFR-3215
Story | CONFR-3144 |  | Requirements: Connect_Driver_Driver Details_PC_FA (BR's and UW Issues) |  |  | Handled in CONFR-3218